## Sheet1
Final Project Gantt Chart |  |  |  | Week Number
[5 empty] | Term 1 | [12 empty] | Xmas |  |  | Exam |  | Term 2
Milestone | Start Date | End Date | Duration | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 24 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Complete Project & Meetings | 2013-09-09 | 2014-04-10 | 30 Weeks
Initial Research | 2013-09-09 | 2013-10-03 | 4 Weeks
Preliminary Research | 2013-09-09 | 2013-10-03 | 4 Weeks
Proposal Draft | 2013-09-16 | 2013-09-23 | 2 Weeks
Final Proposal | 2013-09-23 | 2013-10-03 | 2 Weeks
Software Engineering | 2013-10-03 | 2013-10-31 | 5 Weeks
Interim Report | 2013-10-03 | 2013-10-31 | 5 Weeks
Project Plan | 2013-10-03 | 2013-10-08 | 1 Week
Project Background and Introduction | 2013-10-03 | 2013-10-14 | 2 Weeks
Professional Considerations | 2013-10-07 | 2013-10-14 | 1 Week
Requirements Analysis | 2013-10-07 | 2013-10-21 | 2 Weeks
UML & Game Design Document | 2013-10-14 | 2013-10-31 | 3 Weeks
Implementation | 2013-10-31 | 2014-04-10 | 23 Weeks
Initial Version | 2013-10-31 | 2013-11-25 | 3 Weeks
Version 2 | 2013-11-25 | 2013-12-16 | 3 Weeks
Version 3 | 2013-12-16 | 2014-01-06 | 3 Weeks
Completed Primary Objectives | 2014-01-06 | 2014-01-27 | 3 Weeks
Extensions | 2014-01-27 | 2014-03-13 | 8 Weeks
Bugfixing | 2014-02-24 | 2014-03-13 | 2 Weeks
Polish and Refinement | 2014-02-24 | 2014-03-13 | 2 Weeks
Report
Draft Report | 2014-01-27 | 2014-03-13 | 8 Weeks
Section 1 - Intro/Aims/Research | 2014-01-27 | 2014-02-03 | 2 Weeks
Section 2 - Implementation | 2014-02-03 | 2014-02-17 | 2 Weeks
Section 3 - Evaluation & Testing | 2014-02-17 | 2014-03-03 | 2 Weeks
Section 4 - Conlusion & Future Work | 2014-03-03 | 2014-03-13 | 2 Weeks
Appendixes & Misc | 2014-03-10 | 2014-03-13 | 1 Week
Final Revision | 2014-03-13 | 2014-04-10 | 4 Weeks
Key: | Colour
Period of Work
Final Deadlines
Completed Version Revision
Project Meetings